## BP Actions
Color code and definition
[15 empty] | 1 | 1 | Define
[15 empty] | 2 | 2 | Plan
[15 empty] | 3 | 3 | Communicate
[15 empty] | 4 | 4 | Do
[15 empty] | 5 | 5 | Follow-up
BSC | # | BSC Perspective | BSC Focus area | CSF Type | CSF Title | CSF and Actions | Impact | Responsible | Participants | Start | Finish | Comments | Completion rate |  | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
| 1 | Finance | Even better cost management | JYSK | Fit for the future | Fit for the future |  | SSUC
| 1.1 | Finance | Even better cost management | JYSK | Fit for the future | Reduce Staff cost |  | SSUC
| 1.1.1 | Finance | Even better cost management | JYSK | Fit for the future | Quarterly optimise number of employees based on turnover | Index productivity (JSI 109,5; JHR 106,9; JBA 109,6; JRS 109,3; JWB 108,7) | SSUC | CD, HOR | W46 | W21 |  |  |  | Follow-up 46: 5; Follow-up 8: 5; Follow-up 21: 5
| 1.1.2 | Finance | Even better cost management | JYSK | Fit for the future | Refresh staff clothes policy and follow up on ordering and costs | Clothes saving -7.000 eur | SSUC | SCM | W36 | W21 |  |  |  | 5 36: 1; 5 37: 2; Follow-up 39: 4; Follow-up 46: 5; Follow-up 8: 5; Follow-up 21: 5
| 1.2 | Finance | Even better cost management | JYSK | Fit for the future | Reduce Premise cost by reducing electricity consumption | Electricity saving -28.000 eur | SSUC
| 1.2.1 | Finance | Even better cost management | JYSK | Fit for the future | Define 10% bottom stores in electricity consumption on quarterly base |  | SSUC | FC, RC | W46 | W21 |  |  |  | Follow-up 46: 3; Follow-up 8: 3; Follow-up 21: 3
| 1.2.2 | Finance | Even better cost management | JYSK | Fit for the future | Define actions to reduce consumption |  | SSUC | FC, RC | W47 | W25 |  |  |  | Follow-up 47: 4; Follow-up 48: 4; Follow-up 49: 4; Follow-up 50: 4; Follow-up 9: 4; Follow-up 10: 4; Follow-up 11: 4; Follow-up 12: 4; Follow-up 22: 4; Follow-up 23: 4; Follow-up 24: 4; Follow-up 25: 4
| 1.2.3 | Finance | Even better cost management | JYSK | Fit for the future | Quarterly follow up on improvment |  | SSUC | FC, RC | W46 | W21 |  |  |  | Follow-up 46: 5; Follow-up 8: 5; Follow-up 21: 5
| 1.3 | Finance | Even better cost management | JYSK | Fit for the future | Reduce Premise cost by reducing waste costs | Waste saving -19.000 | SSUC
| 1.3.1 | Finance | Even better cost management | JYSK | Fit for the future | Choose one bottom store per district and analyze consumption |  | SSUC | RC | W46 | W21 |  |  |  | Follow-up 46: 3; Follow-up 8: 3; Follow-up 21: 3
| 1.3.2 | Finance | Even better cost management | JYSK | Fit for the future | Define actions to reduce consumption |  | SSUC |  | W47 | W25 |  |  |  | Follow-up 47: 4; Follow-up 48: 4; Follow-up 49: 4; Follow-up 50: 4; Follow-up 9: 4; Follow-up 10: 4; Follow-up 11: 4; Follow-up 12: 4; Follow-up 22: 4; Follow-up 23: 4; Follow-up 24: 4; Follow-up 25: 4
| 1.3.3 | Finance | Even better cost management | JYSK | Fit for the future | Quarterly follow up on improvment |  | SSUC | FC, RC | W46 | W21 |  |  |  | Follow-up 46: 5; Follow-up 8: 5; Follow-up 21: 5
| 1.4 | Finance | Even better cost management | JYSK | Fit for the future | Reduce Premise cost by focusing on maintenance costs | Maintenance saving -22.000 | SSUC
| 1.4.1 | Finance | Even better cost management | JYSK | Fit for the future | Analyse number of regular store visits and supplier conditions |  | SSUC |  | W35 | W38 |  |  | 1 | 5 36: 2
| 1.4.2 | Finance | Even better cost management | JYSK | Fit for the future | Prepare actions according to findings from analyse |  | SSUC | OA | W35 | W38 |  |  |  | 5 37: 4
| 1.5 | Finance | Even better cost management | JYSK | Fit for the future | Reduce administrative cost | Stationary saving -25.000 | SSUC
| 1.5.1 | Finance | Even better cost management | JYSK | Fit for the future | Prepare guideline for new office supplies supplier |  | SSUC | OA | W36 | W38 |  |  | 1 | 5 36: 2; Follow-up 38: 3
| 1.5.2 | Finance | Even better cost management | JYSK | Fit for the future | Send to DM's consumption of office supplies by stores and follow up on quarterly base |  | SSUC | RC | W39 | W21 |  |  |  | Follow-up 39: 5; Follow-up 46: 5; Follow-up 8: 5; Follow-up 21: 5
| 1.6 | Finance | Even better cost management | JYSK | Fit for the future | Reduce investment costs | Investment savings - 50.000 eur | SSUC
| 1.6.1 | Finance | Even better cost management | JYSK | Fit for the future | Put additional focus on investement costs by regulary benchmark of external supplier prices |  | SSUC |  | W39 | W24 |  |  |  | Follow-up 39: 4; Follow-up 41: 4; Follow-up 46: 4; Follow-up 50: 4; Follow-up 3: 4; Follow-up 8: 4; Follow-up 12: 4; Follow-up 16: 4; Follow-up 21: 4; Follow-up 24: 4
| 2 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Optimise Retail Operations | Index productivity (JSI 109,5; JHR 106,9; JBA 109,6; JRS 109,3; JWB 108,7) | DEL
| 2.1 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Implement new goals setup |  | DEL
| 2.1.1 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Prepare training/communication materials for new goals/KPI setup |  | DEL | RC, DM, SM | W35 | W36 |  |  | 1 | 5 36: 2
| 2.1.2 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Present and train DMs (National Retail Meeting) and SMs (Country SM meeting) |  | DEL | RC, DM, SM | W37 | W39 |  |  |  | 5 37: 4; Follow-up 39: 4
| 2.1.3 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | SMs present and train all store staff |  | DEL | RC, DM, SM | W40 | W44 |  |  |  | Follow-up 40: 4; Follow-up 41: 4; Follow-up 42: 4; Follow-up 43: 4; Follow-up 44: 4
| 2.1.4 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | DMs follow up on understanding during GSM days |  | DEL | RC, DM, SM | W45 | W18 |  |  |  | Follow-up 45: 5; Follow-up 46: 5; Follow-up 47: 5; Follow-up 48: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 51: 5; Follow-up 52: 5; Follow-up 1: 5; Follow-up 2: 5; Follow-up 3: 5; Follow-up 4: 5; Follow-up 5: 5; Follow-up 6: 5; Follow-up 7: 5; Follow-up 8: 5; Follow-up 9: 5; Follow-up 10: 5; Follow-up 11: 5; Follow-up 12: 5; Follow-up 13: 5; Follow-up 14: 5; Follow-up 15: 5; Follow-up 16: 5; Follow-up 17: 5; Follow-up 18: 5
| 2.2 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Optimise store communication |  | DEL
| 2.2.1 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Define 1 store communication ambassador (RM) per country and describe the new role |  | DEL | RM, DM | W35 | W36 |  |  | 1 | 5 36: 2
| 2.2.2 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Present new role to admin users and train them in correct usage of all communication channels |  | DEL | RM, DM | W38 | W38 |  |  |  | 5 37: 3
| 2.2.3 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Store communication ambassador analyse once per quarter all communication to the stores |  | DEL | RM, DM | W45 | W32 |  |  |  | Follow-up 45: 5; Follow-up 8: 5; Follow-up 21: 5; Follow-up 32: 5
| 2.2.4 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Present results to admin users and refresh knowledge about communication to the stores |  | DEL | RM, DM | W45 | W32 |  |  |  | Follow-up 45: 3; Follow-up 8: 3; Follow-up 21: 3; Follow-up 32: 3
| 2.3 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Minimise locally implemented procedures |  | DEL
| 2.3.1 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Create list of all locally implemented procedures |  | DEL | RSS, DM, IA | W35 | W35 |  |  | 1
| 2.3.2 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Go through all and define which can be removed and how to improve locally implemented procedures which needs to stay |  | DEL | RSS, DM, IA | W36 | W36 |  |  |  | 5 36: 2
| 2.3.3 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | Communicate and train on SM meetings in district |  | DEL | RSS, DM, IA | W37 | W39 |  |  |  | 5 37: 4; Follow-up 39: 4
| 2.3.4 | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | DM follow up during AS (local focus area) on implementation |  | DEL | RSS, DM, IA | W52 | W12 |  |  |  | Follow-up 52: 5; Follow-up 1: 5; Follow-up 2: 5; Follow-up 9: 5; Follow-up 10: 5; Follow-up 11: 5; Follow-up 12: 5
| 3 | Employees & learning | Attractive place to work | JYSK | Attract the future | Attract the future |  | JCU
| 3.1 | Employees & learning | Attractive place to work | JYSK | Attract the future | Improve communication of benefits internally and externally | STO total (JSI/JBA/JRS < 20; JHR < 15) | JCU
| 3.1.1 | Employees & learning | Attractive place to work | JYSK | Attract the future | Define list of relevant benefits per country and prepare communication plan with country specific defined channels |  | JCU | HR | W40 | W42 |  |  |  | Follow-up 40: 1; Follow-up 41: 2; Follow-up 42: 3
| 3.1.2 | Employees & learning | Attractive place to work | JYSK | Attract the future | Adjust job ads and storytelling for better benefit communication/visibility |  | JCU | HRBP's, ComM | W45 | W45 |  |  |  | Follow-up 45: 4
| 3.1.3 | Employees & learning | Attractive place to work | JYSK | Attract the future | Monthly evaluate number of applicants and quality according to rating in SmartRecruiters and adjust communication accordingly |  | JCU | HRBP's | W45 | W27 |  |  |  | Follow-up 45: 5; Follow-up 49: 5; Follow-up 1: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 14: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5
| 3.1.4 | Employees & learning | Attractive place to work | JYSK | Attract the future | Quarterly follow up on CMT |  | JCU | HRM | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 3.2 | Employees & learning | Attractive place to work | JYSK | Attract the future | Secure quality of recruitment process | STO new employees (JSI/JRS < 25; JHR/JBA < 20) | JCU
| 3.2.1 | Employees & learning | Attractive place to work | JYSK | Attract the future | Increase focus on preffered profile, critical job factors and potential by DM/HRBP challenge every new employment and internal promotion |  | JCU | HRBP's, RM's, DM's | W35 | W37 |  |  | 1 | 5 36: 2; 5 37: 3
| 3.2.2 | Employees & learning | Attractive place to work | JYSK | Attract the future | Relaunch refferal program on SM meeting and HO kick off to increase quality of candidates and engagement of employees |  | JCU | HRM | W37 | W39 |  |  |  | 5 37: 4; Follow-up 39: 4
| 3.2.3 | Employees & learning | Attractive place to work | JYSK | Attract the future | Monthly present and discuss profiles of new employees and internal promotions on MRM |  | JCU | HRBP's. RM's | W41 | W27 |  |  |  | Follow-up 41: 5; Follow-up 45: 5; Follow-up 50: 5; Follow-up 3: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 15: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5
| 3.2.4 | Employees & learning | Attractive place to work | JYSK | Attract the future | Non preferred profile employement/promotions must be approved by HRM/HOR |  | JCU | HRBP's. RM's | W37 | W35
| 3.3.5 | Employees & learning | Attractive place to work | JYSK | Attract the future | Quarterly follow up on preffered profiles on CMT |  | JCU | HRM | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 3.3 | Employees & learning | Attractive place to work | JYSK | Attract the future | Build Influencer Team to secure strong engagement | TTH < 30 | JCU
| 3.3.1 | Employees & learning | Attractive place to work | JYSK | Attract the future | Define selection process of influencers, level of involvement and goals of the team |  | JCU | ComM, HR | W35 | W39 |  |  | 1 | 5 36: 2; 5 37: 3; Follow-up 39: 3
| 3.3.2 | Employees & learning | Attractive place to work | JYSK | Attract the future | Train Influencer Team and align cross country on targets and channels |  | JCU | ComM, HR | W41 | W41 |  |  |  | Follow-up 41: 4
| 3.3.3 | Employees & learning | Attractive place to work | JYSK | Attract the future | Quarterly organize planning meetings for Influencer Team with tasks, goals and planned projects and campaigns |  | JCU | ComM, HR | W4 | W14 |  |  |  | Follow-up 4: 4; Follow-up 14: 4
| 3.3.4 | Employees & learning | Attractive place to work | JYSK | Attract the future | Quarterly evaluate campaign success and KPI's and adjust actions in EB calendar |  | JCU | ComM, HR | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Retain and empower our talent and performers |  | JCU
| 4.1 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Roll out of new Learning Management System and Performance Managment system | STO DepSM (JSI/JBA/JRS < 20; JHR < 15) | JCU
| 4.1.1 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Prepare roll out plan and communicate on NRM and SM meeting |  | JCU | HRM | W35 | W39 |  |  | 1 | 5 36: 2; 5 37: 3; Follow-up 39: 3
| 4.1.2 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | HR train DM's on MRM |  | JCU | HRBP's | W3 | W3 |  |  |  | Follow-up 3: 4
| 4.1.3 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | DM's train SM's |  | JCU | DM's | W4 | W5 |  |  |  | Follow-up 4: 4; Follow-up 5: 4
| 4.1.4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Follow up on roll out and implementation by HRBP's and DM's in Q3 and Q4 |  | JCU | HRBP's, DM's | W9 | W35 |  |  |  | Follow-up 12: 5; Follow-up 24: 5
| 4.2 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Improve new employee Onboarding process | STO new employees (JSI/JRS < 25; JHR/JBA < 20) | JCU
| 4.2.1 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Secure follow up on onboarding process by DM/HRBP/RM during 3 AS rounds, DM/HRBP operational days and RM/HRBP operational days |  | JCU | HRBP's, DM's, RM's |  |  | Define local AS rounds (IPR)
| 4.2.2 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Quarterly present onboarding survey results on MRM and define actions |  | JCU | HRBP's, DM's | W41 | W19 |  |  |  | Follow-up 41: 5; Follow-up 50: 5; Follow-up 10: 5; Follow-up 19: 5
| 4.2.3 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Twice a year HoR and HRM follow up on onboarding process OTR with prepared check list and survey results |  | JCU | HoR, HRM | W59 | W10 |  |  |  | Follow-up 50: 4; Follow-up 10: 4
| 4.2.4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Quarterly follow up on CMT |  | JCU | HRM | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 4.3 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Improve mentoring and follow up of Talents and SMT's | IFR SM > 80; IFR DepSM > 70 | JCU
| 4.3.1 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Organize twice a year WS with mentors for Talents and twice a year WS with mentors for SMT's to align on process and quality of mentoring |  | JCU | HRBP, DM | W41 | W14 |  |  |  | Follow-up 41: 1; Follow-up 42: 2; Follow-up 43: 3; Follow-up 44: 4; Follow-up 52: 1; Follow-up 1: 2; Follow-up 2: 3; Follow-up 3: 4; Follow-up 6: 4; Follow-up 11: 1; Follow-up 12: 2; Follow-up 13: 3; Follow-up 14: 4
| 4.3.2 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | On MRM present status of Talents and SMT's after 1st modul of Talent programe and each modul of SMT programe |  | JCU | HRBP, RM | W45 | W24 |  |  |  | Follow-up 45: 5; Follow-up 6: 5; Follow-up 15: 5; Follow-up 23: 5
| 4.3.3 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Twice a year HoR and HRM follow up on talents and SMT's OTR with prepared overview |  | JCU | HoR, HRM | W50 | W10 |  |  |  | Follow-up 50: 4; Follow-up 10: 4
| 4.3.4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Quarterly follow up on CMT |  | JCU | HRM | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 4.4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Secure IO fulfilment and quality | STO DepSM (JSI/JBA/JRS < 20; JHR < 15) | JCU
| 4.4.1 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Present current status of IO fulfilment and percentage of preffered profiles on NRM and SM meeting in September to show reality check and secure focus |  | JCU | HoR, HRM | W35 | W39 |  |  | 1 | 5 36: 2; 5 37: 3; Follow-up 39: 3
| 4.4.2 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Monthly on MRM and MCRM present IO fullfilment and preffered profiles of employees on all levels |  | JCU | HRBP's, HoR | W40 | W27 |  |  |  | Follow-up 40: 5; Follow-up 41: 5; Follow-up 45: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 2: 5; Follow-up 3: 5; Follow-up 5: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 14: 5; Follow-up 15: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5
| 4.4.3 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Prepare actions for IO fulfilment and prefferred profile status according to results |  | JCU | DM's, HRBP's | W41 | W27 |  |  |  | Follow-up 41: 4; Follow-up 45: 4; Follow-up 50: 4; Follow-up 3: 4; Follow-up 6: 4; Follow-up 10: 4; Follow-up 15: 4; Follow-up 19: 4; Follow-up 23: 4; Follow-up 27: 4
| 4.4.4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Quarterly follow up on CMT and every second month HoR and HRM |  | JCU | HRM, HoR | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 4.5 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Launch wellbeing program for employees | STO total (JSI/JBA/JRS < 20; JHR < 15) | JCU
| 4.5.1 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Define topics and yearly wellbeing calendar - 5 months per FY we'll have wellbeing topic (How to eat healthy at work, How to deal with stress, financial literacy, Benefits of regular excersize ...) During those months we'll organize webinars on defined topis for all employees and post blogs and vlogs intenally. |  | JCU | HR | W35 | W39 |  |  | 1 | 5 36: 2; 5 37: 3; Follow-up 39: 3
| 4.5.2 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Prepare communication plan: internally to promote wellbeing program and announce webinars and externally to promote additional benefits of working in JYSK |  | JCU | HR, ComM | W38 | W39 |  |  |  | 5 37: 4; Follow-up 39: 4
| 4.5.3 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Prepare landing page for wellbeing materials for employees and promotional materials for external communication |  | JCU | ComM, HR | W37 | W37 |  |  |  | 5 37: 4
| 4.5.4 | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | Follow up on execution and adapt plan and communication |  | JCU | HR | W49 | W24 |  |  |  | Follow-up 49: 5; Follow-up 12: 5; Follow-up 24: 5
| 5 | Finance | Sales growth | Service function | Explore, implement and leverage Artificial Intelligence | Explore, implement and leverage Artificial Intelligence
| 5.1 | Finance | Sales growth | Service Function | Explore, implement and leverage Artificial Intelligence | Action
| 5.1.1 | Finance | Sales growth | Service Function | Explore, implement and leverage Artificial Intelligence | Sub-action
| 5.2 | Finance | Sales growth | Service Function | Explore, implement and leverage Artificial Intelligence | Action
| 6 | Finance | Sales growth | Service function | Secure the voice of the customer through insights | Secure the voice of the customer through insights
| 6.1 | Finance | Sales growth | Service Function | Secure the voice of the customer through insights | Action
| 6.1.1 | Finance | Sales growth | Service Function | Secure the voice of the customer through insights | Sub-action
| 6.2 | Finance | Sales growth | Service Function | Secure the voice of the customer through insights | Action
| 7 | Finance | Sales growth | Service function | Make JYSK more sustainable | Make JYSK more sustainable
| 7.1 | Finance | Sales growth | Service Function | Make JYSK more sustainable | Action
| 7.1.1 | Finance | Sales growth | Service Function | Make JYSK more sustainable | Sub-action
| 7.2 | Finance | Sales growth | Service Function | Make JYSK more sustainable | Action
| 8 | Finance | Sales growth | Service function | Enhance benefits from RTM | Enhance benefits from RTM
| 8.1 | Finance | Sales growth | Service Function | Enhance benefits from RTM | Action
| 8.1.1 | Finance | Sales growth | Service Function | Enhance benefits from RTM | Sub-action
| 8.2 | Finance | Sales growth | Service Function | Enhance benefits from RTM | Action
| 9 | Customer first | Easy shopping | Service function | Upgrade web shops to 3.0 | Upgrade web shops to 3.0
| 9.1 | Customer first | Easy shopping | Service Function | Upgrade web shops to 3.0 | Action
| 9.1.1 | Customer first | Easy shopping | Service Function | Upgrade web shops to 3.0 | Sub-action
| 9.2 | Customer first | Easy shopping | Service Function | Upgrade web shops to 3.0 | Action
| 10 | Internal processes | Balanced flow of goods | Service function | Improve delivery stability and service | Improve delivery stability and service
| 10.1 | Internal processes | Balanced flow of goods | Service function | Improve delivery stability and service | Action
| 10.1.1 | Internal processes | Balanced flow of goods | Service function | Improve delivery stability and service | Sub-action
| 10.2 | Internal processes | Balanced flow of goods | Service function | Improve delivery stability and service | Action
| 11 | Internal processes | Attractive stores | Service function | Simplify communication to stores | Simplify communication to stores
| 11.1 | Internal processes | Attractive stores | Service function | Simplify communication to stores | Action
| 11.1.1 | Internal processes | Attractive stores | Service function | Simplify communication to stores | Sub-action
| 11.2 | Internal processes | Attractive stores | Service function | Simplify communication to stores | Action
| 12 | Internal processes | Effective marketing | Service function | Improve situation-based marketing and branding | Improve situation-based marketing and branding
| 12.1 | Internal processes | Effective marketing | Service function | Improve situation-based marketing and branding | Action
| 12.1.1 | Internal processes | Effective marketing | Service function | Improve situation-based marketing and branding | Sub-action
| 12.2 | Internal processes | Effective marketing | Service function | Improve situation-based marketing and branding | Action
| 13 | Internal processes | Effective marketing | Service function | Make “Great offers” more visible | Make “Great offers” more visible
| 13.1 | Internal processes | Effective marketing | Service function | Make “Great offers” more visible | Action
| 13.1.1 | Internal processes | Effective marketing | Service function | Make “Great offers” more visible | Sub-action
| 13.2 | Internal processes | Effective marketing | Service function | Make “Great offers” more visible | Action
| 14 | Customer First | Easy shopping | Local | Improve online performance | Improve online performance | Online sales index (JSI 110, JHR 110, JBA/JRS 115) OOPUS Share >2,0% C&C Share of orders picked within 30 min 98,0 | IPR
| 14.1 | Customer First | Easy shopping | Local | Improve online performance | Secure even stronger external communication |  | IPR
| 14.1.1 | Customer First | Easy shopping | Local | Improve online performance | Organise working group to prepare detailed communication and promoting plan for online sales channels (radio, flyers, in-store, online, pr…) |  | IPR | CoMM | W36 | W37 |  |  | 1 | 5 36: 2
| 14.1.2 | Customer First | Easy shopping | Local | Improve online performance | Insert headline in CP during DCP campaigns to promote online sales channels |  | IPR | RHOS; SMM | W36 | W37 |  |  | 1 | 5 36: 2
| 14.1.3 | Customer First | Easy shopping | Local | Improve online performance | Promote in-store Online campaign activities (Free Freight and Cyber days) |  | IPR | SoMe; RHOS, SMM | W36 | W37 |  |  | 1 | 5 36: 2; 5 37: 4
| 14.1.4 | Customer First | Easy shopping | Local | Improve online performance | Implement promoting Online sales tell message and define how to promote JYSK Online advantages |  | IPR | SMM; RHOS; CoMM | W36 | W38 |  |  | 1 | 5 36: 2; 5 37: 4
| 14.1.5 | Customer First | Easy shopping | Local | Improve online performance | Three times per month include C&C and OOPUS in IG stories and add IG highlight with steps for C&C and OOPUS shopping |  | IPR | SOME; CoMM | W36 | W35 |  |  | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 14.1.6 | Customer First | Easy shopping | Local | Improve online performance | After each new opening in a new city, include insertion in the first regular CP: "We opened our store at [address], near you, but you can also shop online at JYSK.si/hr/ba/rs." |  | IPR | SMM | W36 | W35 |  |  | 1 | 5 36: 2
| 14.2 | Customer First | Easy shopping | Local | Improve online performance | Increase awareness and knowledge on Online sales and improve internally communication |  | IPR
| 14.2.1 | Customer First | Easy shopping | Local | Improve online performance | Adjust CSC Training materials for stores on topic: What are the benefits for customers if purchase online, C&C or OOPUS? and upgrade S&S with its. |  | IPR | HR; CSM | W35 | W36 |  |  | 1 | 5 36: 2
| 14.2.2 | Customer First | Easy shopping | Local | Improve online performance | Conduct upgraded S&S training in all stores |  | IPR | DM; SM | W35 | W10 |  |  | 4 | Follow-up 10: 4
| 14.2.3 | Customer First | Easy shopping | Local | Improve online performance | Follow up on knowledge during GSM days in Round 1 and Round 2 |  | IPR | DM | W36 | W19 |  |  | 5 | 5 36: 5; 5 37: 5; Follow-up 38: 5; Follow-up 39: 5; Follow-up 40: 5; Follow-up 41: 5; Follow-up 42: 5; Follow-up 43: 5; Follow-up 44: 5; Follow-up 45: 5; Follow-up 46: 5; Follow-up 47: 5; Follow-up 48: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 51: 5; Follow-up 52: 5
| 14.2.4 | Customer First | Easy shopping | Local | Improve online performance | Monthly publish share of C&C, OOPUS and Online sales on store/district/country level |  | IPR | RC | W35 | W34 |  |  | 5 | Follow-up 40: 5; Follow-up 45: 5; Follow-up 49: 5; Follow-up 1: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 14: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5; Follow-up 32: 5
| 14.3 | Customer First | Easy shopping | Local | Improve online performance | Secure fast Onboarding for all new hires in regards with Online sales |  | IPR
| 14.3.1 | Customer First | Easy shopping | Local | Improve online performance | Prepare training what will be held for new staff in SOL |  | IPR | HR; RM | W35 | W39 |  |  | 1 | 5 36: 2; 5 37: 3; Follow-up 39: 3
| 14.3.2 | Customer First | Easy shopping | Local | Improve online performance | TTT SMs in SOL stores |  | IPR | HR | W43 | W43 |  |  |  | Follow-up 43: 4
| 14.3.3 | Customer First | Easy shopping | Local | Improve online performance | Conduct training for all new staff in SOL |  | IPR | SMM | W44 | W35 | [11 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 14.3.4 | Customer First | Easy shopping | Local | Improve online performance | Follow up during regular On-boarding follow up |  | IPR | DM; RM; HR | W44 | W35 | [11 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| 14.4 | Customer First | Easy shopping | Local | Improve online performance | Test SOT valid online only and promote JYSK online sales channels |  | IPR
| 14.4.1 | Customer First | Easy shopping | Local | Improve online performance | Prepare all materials (incl prices) for SOT valid online only and press conference |  | IPR | SMM; RHOS | W37 | W38 |  |  |  | 5 36: 1; 5 37: 2; Follow-up 39: 3
| 14.4.2 | Customer First | Easy shopping | Local | Improve online performance | During Annual party activate (when stores are closed) SOT valid Online only in JBA/JRS |  | IPR | SMM; RHOS | W45 | W45 |  |  |  | Follow-up 45: 4
| 14.4.3 | Customer First | Easy shopping | Local | Improve online performance | Organise press to promote Online only SOT (+ EB) |  | IPR | CoMM | W44 | W44 |  |  |  | Follow-up 44: 4
| 14.4.4 | Customer First | Easy shopping | Local | Improve online performance | Evaluate results together with S&E |  | IPR | RHOS; SMM; HOR | W3 | W3 |  |  |  | Follow-up 3: 5
| 14.4.5 | Customer First | Easy shopping | Local | Improve online performance | Align about next activation according to results of test |  | IPR | RHOS; SMM; HOR | W3 | W3 |  |  |  | Follow-up 3: 4
| 15 | Internal processes | Attractive stores | Local | Optimize stock in stores | Optimize stock in stores | Stock index JWB 95 Stock turnover index 110 Index stock Clearance 80 | MSTEV
| 15.1 | Internal processes | Attractive stores | Local | Optimize stock in stores | Improve allocation process and better alingment between Retail, S&E and FoG about seasonal articles |  | MSTEV
| 15.1.1 | Internal processes | Attractive stores | Local | Optimize stock in stores | Organise regular meeting with S&E to align about seasonal allocation quantites and flow for Xmas and Outdoor season |  | MSTEV | RM; RHOS; SAM | W40 | W14 |  |  |  | Follow-up 40: 4; Follow-up 3: 4; Follow-up 14: 4
| 15.1.2 | Internal processes | Attractive stores | Local | Optimize stock in stores | Secure feedback and alignment with FoG about most important seasonal articles, quantities and flow |  | MSTEV | RM; RHOS; SAM; FoG | W40 | W14 |  |  |  | 5 36: 1; 5 37: 2; Follow-up 38: 3; Follow-up 40: 4; Follow-up 3: 4; Follow-up 14: 4
| 15.1.3 | Internal processes | Attractive stores | Local | Optimize stock in stores | Follow up on all allocation of seasonal and campaign articles during Quarterly meetings (Retail/S&E) |  | MSTEV | RM; RHOS; SAM | W40 | W14 |  |  |  | Follow-up 40: 5; Follow-up 3: 5; Follow-up 14: 5
| 15.2 | Internal processes | Attractive stores | Local | Optimize stock in stores | Secure optimal stock level before and during Xmas and garden seasons |  | MSTEV
| 15.2.1 | Internal processes | Attractive stores | Local | Optimize stock in stores | Prepare training for SM how to maintaine optimal stock level of seasonal articles and how to secure constant focus |  | MSTEV | RM; HR | W35 | W36 |  |  | 1 | 5 36: 2
| 15.2.2 | Internal processes | Attractive stores | Local | Optimize stock in stores | On SM meeting in September present project steps and conduct training for XMAS |  | MSTEV | RM | W39 | W39 |  |  |  | Follow-up 39: 4
| 15.2.3 | Internal processes | Attractive stores | Local | Optimize stock in stores | On Regional SM meeting in March conduct training for Garden (incl. Learnings from Xmas) |  | MSTEV | RM | W11 | W11 |  |  |  | Follow-up 11: 4
| 15.2.4 | Internal processes | Attractive stores | Local | Optimize stock in stores | Follow up throught local focus area in Campain and commercial follow up in period between W42 - W1 (XMAS) and W15 - W31 (Garden) |  | MSTEV | DM | W42 | W31 |  |  |  | Follow-up 42: 5; Follow-up 43: 5; Follow-up 44: 5; Follow-up 45: 5; Follow-up 46: 5; Follow-up 47: 5; Follow-up 48: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 51: 5; Follow-up 52: 5; Follow-up 1: 5; Follow-up 15: 5; Follow-up 16: 5; Follow-up 17: 5; Follow-up 18: 5; Follow-up 19: 5; Follow-up 20: 5; Follow-up 21: 5; Follow-up 22: 5; Follow-up 23: 5; Follow-up 24: 5; Follow-up 25: 5; Follow-up 26: 5; Follow-up 27: 5; Follow-up 28: 5; Follow-up 29: 5; Follow-up 30: 5; Follow-up 31: 5
| 15.3 | Internal processes | Attractive stores | Local | Optimize stock in stores | Improve working with SMA and clearance articles |  | MSTEV
| 15.3.1 | Internal processes | Attractive stores | Local | Optimize stock in stores | Prepare short in-store training for SM how to work with SMA and clearance articles in stores |  | MSTEV | RM; HR; RSS | W35 | W40 |  |  | 1 | 5 36: 2; Follow-up 39: 3; Follow-up 40: 3
| 15.3.2 | Internal processes | Attractive stores | Local | Optimize stock in stores | RM together with RSS create plan for visiting all stores and conducting in-store training |  | MSTEV | RM; RSS | W40 | W40 |  |  |  | Follow-up 40: 4
| 15.3.3 | Internal processes | Attractive stores | Local | Optimize stock in stores | Roll out in-store training in two phases (RSS with SM and SM with SA) |  | MSTEV | RM; RSS | W41 | W5 |  |  |  | Follow-up 41: 4; Follow-up 42: 4; Follow-up 43: 4; Follow-up 44: 4; Follow-up 45: 4; Follow-up 46: 4; Follow-up 47: 4; Follow-up 48: 4; Follow-up 49: 4; Follow-up 50: 4; Follow-up 51: 4; Follow-up 52: 4; Follow-up 1: 4; Follow-up 2: 4; Follow-up 3: 4; Follow-up 4: 4; Follow-up 5: 4
| 15.3.4 | Internal processes | Attractive stores | Local | Optimize stock in stores | Monthly follow on 20% bottom stores by DM based on SMA and Clearance report |  | MSTEV | DM | W41 | W35 |  |  |  | Follow-up 40: 5; Follow-up 45: 5; Follow-up 49: 5; Follow-up 1: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 14: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5; Follow-up 32: 5
| 15.3.5 | Internal processes | Attractive stores | Local | Optimize stock in stores | Follow up during Operational days and MRM by RMs |  | MSTEV | RM | W41 | W35 |  |  |  | Follow-up 40: 5; Follow-up 41: 5; Follow-up 45: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 2: 5; Follow-up 3: 5; Follow-up 5: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 14: 5; Follow-up 15: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5
| 15.4 | Internal processes | Attractive stores | Local | Optimize stock in stores | Secure common focus from S&E and retail to improve stock quality |  | MSTEV
| 15.4.1 | Internal processes | Attractive stores | Local | Optimize stock in stores | Define agenda for monthly "stock quality meeting" (RHOS, SAM, SAC, RM) |  | MSTEV | RM; RHOS | W35 | W40 |  |  | 1 | 5 36: 2; Follow-up 40: 3
| 15.4.2 | Internal processes | Attractive stores | Local | Optimize stock in stores | Conduct monthly meeting and comunicate aligned actions to all involved parties |  | MSTEV | RM; RHOS, SAM | W40 | W32 |  |  |  | Follow-up 40: 4; Follow-up 45: 4; Follow-up 49: 4; Follow-up 1: 4; Follow-up 6: 4; Follow-up 10: 4; Follow-up 14: 4; Follow-up 19: 4; Follow-up 23: 4; Follow-up 27: 4; Follow-up 32: 4
| 15.4.3 | Internal processes | Attractive stores | Local | Optimize stock in stores | Follow up on next monthly meeting and if needed through local focus areas |  | MSTEV | RM; RHOS, SAM | W45 | W32 |  |  |  | Follow-up 45: 5; Follow-up 49: 5; Follow-up 1: 5; Follow-up 6: 5; Follow-up 10: 5; Follow-up 14: 5; Follow-up 19: 5; Follow-up 23: 5; Follow-up 27: 5; Follow-up 32: 5
| 16 | Finance | Sales growth | Local | Increase number of customers | Increase number of customers | Customer index 105 | IOP
| 16.1 | Finance | Sales growth | Local | Increase number of customers | Increase number of customers through trainings |  | IOP
| 16.1.1 | Finance | Sales growth | Local | Increase number of customers | Prepare "Right Sales Attitude" training materials (including Customer conversion) |  | IOP | HR, RSS, DM, SM | W35 | W39 |  |  | 1 | 5 36: 2; Follow-up 39: 3
| 16.1.2 | Finance | Sales growth | Local | Increase number of customers | Train DepSMs on DepSM meeting |  | IOP | HR, RSS, DM, SM | W41 | W41 |  |  |  | Follow-up 41: 4
| 16.1.3 | Finance | Sales growth | Local | Increase number of customers | DepSM train stores in Q1 and Q3 (Nov, May) |  | IOP | HR, RSS, DM, SM | W41 | W21 |  |  |  | Follow-up 43: 4; Follow-up 44: 4; Follow-up 45: 4; Follow-up 46: 4; Follow-up 18: 4; Follow-up 19: 4; Follow-up 20: 4; Follow-up 21: 4
| 16.1.4 | Finance | Sales growth | Local | Increase number of customers | Follow up on training quality through sales attitude report and reality check through Campaign and commercial follow up local focus area |  | IOP | HR, RSS, DM, SM | W46 | W29 |  |  |  | Follow-up 46: 5; Follow-up 47: 5; Follow-up 48: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 51: 5; Follow-up 52: 5; Follow-up 1: 5; Follow-up 21: 5; Follow-up 22: 5; Follow-up 23: 5; Follow-up 24: 5; Follow-up 25: 5; Follow-up 26: 5; Follow-up 27: 5; Follow-up 28: 5; Follow-up 29: 5
| 16.2 | Finance | Sales growth | Local | Increase number of customers | Increase focus on right sales attitude through competitions |  | IOP
| 16.2.1 | Finance | Sales growth | Local | Increase number of customers | Create materials and rules |  | IOP | DM, SM | W35 | W36 |  |  | 1 | 5 36: 2
| 16.2.2 | Finance | Sales growth | Local | Increase number of customers | Communicate and roll out the competitions (Dec and Jun) |  | IOP | DM, SM | W49 | W27 |  |  |  | Follow-up 49: 4; Follow-up 50: 4; Follow-up 51: 4; Follow-up 52: 4; Follow-up 23: 4; Follow-up 24: 4; Follow-up 25: 4; Follow-up 26: 4
| 16.2.3 | Finance | Sales growth | Local | Increase number of customers | Follow up on results and celebrate winners |  | IOP | RC, DM, SM | W52 | W27 |  |  |  | Follow-up 52: 5; Follow-up 26: 5
| 16.3 | Finance | Sales growth | Local | Increase number of customers | Increase number of customers through better campaign execution |  | IOP
| 16.3.1 | Finance | Sales growth | Local | Increase number of customers | Refresh knowledge on campaign preparation and execution through best practice sharing on Country SM meeting |  | IOP | DM, SM | W35 | W39 |  |  | 1 | 5 36: 2; Follow-up 39: 4
| 16.3.2 | Finance | Sales growth | Local | Increase number of customers | Define most important campaigns on yearly level and organize competitions for employees through internal FB group |  | IOP | RC, DM, SM | W35 | W36 |  |  | 1 | 5 36: 2
| 16.3.3 | Finance | Sales growth | Local | Increase number of customers | Organise Campaign & commercial follow up workshop for DMs at NRM to ensure same approach and alignment |  | IOP | RC, DM, SM | W45 | W46 |  |  |  | Follow-up 45: 4; Follow-up 46: 5
| 17 | Finance | Sales growth | Local | Fight back on mattresses sales | Fight back on mattresses sales | Mattreses index 110 | IOP
| 17.1 | Finance | Sales growth | Local | Fight back on mattresses sales | Increase knowledge about mattresses |  | IOP
| 17.1.1 | Finance | Sales growth | Local | Fight back on mattresses sales | Conduct twice per year mattresses e-learning for all employees |  | IOP | DM,HR,SM | W36 | W9 | September and February |  |  | 5 36: 1; 5 37: 2; Follow-up 38: 3; Follow-up 39: 4; Follow-up 40: 4; Follow-up 5: 4; Follow-up 6: 4; Follow-up 7: 4; Follow-up 8: 4
| 17.1.2 | Finance | Sales growth | Local | Fight back on mattresses sales | Prepare materials and refresh knowledge of usage of code 7 on Country SM meeting and DepSM meeting |  | IOP | RM | W36 | W41 |  |  | 1 | 5 36: 2; Follow-up 38: 4; Follow-up 41: 4
| 17.1.3 | Finance | Sales growth | Local | Fight back on mattresses sales | Conduct training in stores after DepSM meeting |  | IOP | SM, DepSM | W41 | W45 |  |  |  | Follow-up 42: 4; Follow-up 43: 4; Follow-up 44: 4; Follow-up 45: 4
| 17.1.4 | Finance | Sales growth | Local | Fight back on mattresses sales | Follow up on knowledge through Campaign and commercial follow up local focus area in October, and in March after e-learning round |  | IOP | DM | W43 | W13 |  |  |  | Follow-up 43: 5; Follow-up 44: 5; Follow-up 45: 5; Follow-up 46: 5; Follow-up 47: 5; Follow-up 9: 5; Follow-up 10: 5; Follow-up 11: 5; Follow-up 12: 5; Follow-up 13: 5
| 17.2 | Finance | Sales growth | Local | Fight back on mattresses sales | Prepare role plays for stores with focus on sales techniques and specifications |  | IOP
| 17.2.1 | Finance | Sales growth | Local | Fight back on mattresses sales | Prepare role play materials with specific examples |  | IOP | RM, HRM | W36 | W37 |  |  | 1 | 5 36: 2
| 17.2.2 | Finance | Sales growth | Local | Fight back on mattresses sales | Present role plays and roll out plan on Country SM meeting |  | IOP | RM | W36 | W38 |  |  |  | Follow-up 38: 3
| 17.2.3 | Finance | Sales growth | Local | Fight back on mattresses sales | Secure role playing at least on every second Monthly meeting in store according to performance |  | IOP | RM, DM | W38 | W32 |  |  |  | Follow-up 40: 4; Follow-up 49: 4; Follow-up 6: 4; Follow-up 14: 4; Follow-up 23: 4; Follow-up 32: 4
| 17.2.4 | Finance | Sales growth | Local | Fight back on mattresses sales | Include follow up as local focus area in Campaign and commercial follow up |  | IOP | DM | W39 | W35 |  |  |  | Follow-up 41: 5; Follow-up 42: 5; Follow-up 43: 5; Follow-up 44: 5; Follow-up 50: 5; Follow-up 51: 5; Follow-up 52: 5; Follow-up 1: 5; Follow-up 7: 5; Follow-up 8: 5; Follow-up 9: 5; Follow-up 10: 5; Follow-up 15: 5; Follow-up 16: 5; Follow-up 17: 5; Follow-up 18: 5; Follow-up 24: 5; Follow-up 25: 5; Follow-up 26: 5; Follow-up 27: 5; Follow-up 33: 5; Follow-up 34: 5; Follow-up 35: 5
| 17.3 | Finance | Sales growth | Local | Fight back on mattresses sales | Secure costant focus in peak periods through competitions |  | IOP
| 17.3.1 | Finance | Sales growth | Local | Fight back on mattresses sales | Prepare competition and comunicate it during SM meeting in districts |  | IOP | DM | W41 | W46 |  |  |  | Follow-up 41: 1; Follow-up 42: 2; Follow-up 46: 3
| 17.3.2 | Finance | Sales growth | Local | Fight back on mattresses sales | Conduct competitions during December and June with focus on share of Gold mattresses in total mattresses sales |  | IOP | RM | W48 | W26 |  |  |  | Follow-up 48: 4; Follow-up 49: 4; Follow-up 50: 4; Follow-up 51: 4; Follow-up 23: 4; Follow-up 24: 4; Follow-up 25: 4; Follow-up 26: 4
| 17.3.3 | Finance | Sales growth | Local | Fight back on mattresses sales | Ensure regular follow up during the competition |  | IOP | RM | W48 | W26 |  |  |  | Follow-up 48: 5; Follow-up 49: 5; Follow-up 50: 5; Follow-up 51: 5; Follow-up 23: 5; Follow-up 24: 5; Follow-up 25: 5; Follow-up 26: 5
| 17.3.4 | Finance | Sales growth | Local | Fight back on mattresses sales | Publish end results and celebrate winners |  | IOP | RM | W51 | W26 |  |  |  | Follow-up 51: 5; Follow-up 26: 5
Note on B9: Color indicate which BSC perspective and focus area the CSF belongs. No color = missing/wrong input
Note on C9: Indicate as deliverable (whole number) or action to succeed with deliverable (separated with ".").
Note on D9: Select Balanced Scorecard Perspective from drop-down. (linked to BSC Focus area)
Note on E9: Select Balanced Scorecard Focus Area from drop-down. (linked to BSC Perpective)
Note on F9: Select CSF type in drop-down.
Note on G9: Type in CSF title. OBS: Repeat in all rows with actions for CSF, for filter and slicers to work (above).
Note on H9: Example: CSF title (1) and actions + sub-actions to succeed 1) Implement DM 3.0 - CSF from FY20 1.1) DM bi-weekly store visit, 1.2) Introduce new BI reports, 1.3) Use Skype meetings, 1.4) Ensure use of mobiles
Note on I9: Type in expected impact related to the CSF. Can be a KPI or a more broad impact
Note on J9: Name of the responsible person (preferably one)
Note on K9: Type in name of main participant(s) - think "who should be involved"
Note on N9: Use comment field for status on action or CSF.
Note on Q9: Type 1, 2, 3, 4 or 5 to indicate planned actions in calendar weeks.
Note on AA12: Ivan Protega: During P&L meeting 15.11
Note on AO12: Ivan Protega: During P&L meeting 17.02
Note on BB12: Ivan Protega: During P&L meeting 19.05
Note on T13: Ivan Protega: On Country SM meeting
Note on AA13: Ivan Protega: During P&L meeting 15.11
Note on AO13: Ivan Protega: During P&L meeting 17.02
Note on BB13: Ivan Protega: During P&L meeting 19.05
Note on AA15: Ivan Protega: During P&L meeting 15.11
Note on AO15: Ivan Protega: During P&L meeting 17.02
Note on BB15: Ivan Protega: During P&L meeting 19.05
Note on AA17: Ivan Protega: During P&L meeting 15.11
Note on AO17: Ivan Protega: During P&L meeting 17.02
Note on BB17: Ivan Protega: During P&L meeting 19.05
Note on AA19: Ivan Protega: During P&L meeting 15.11
Note on AO19: Ivan Protega: During P&L meeting 17.02
Note on BB19: Ivan Protega: During P&L meeting 19.05
Note on AA21: Ivan Protega: During P&L meeting 15.11
Note on AO21: Ivan Protega: During P&L meeting 17.02
Note on BB21: Ivan Protega: During P&L meeting 19.05
Note on S26: Ivan Protega: On Country SM meeting
Note on T29: Ivan Protega: On "Investment meeting" 23.09
Note on V29: Ivan Protega: On "Investment meeting" 11.10
Note on AA29: Ivan Protega: On "Investment meeting" 15.11
Note on AE29: Ivan Protega: On "Investment meeting" 12.12
Note on AJ29: Ivan Protega: On "Investment meeting" 14.01
Note on AO29: Ivan Protega: On "Investment meeting" 17.02
Note on AS29: Ivan Protega: On "Investment meeting" 18.03
Note on AW29: Ivan Protega: On "Investment meeting" 14.04
Note on BB29: Ivan Protega: On "Investment meeting" 19.05
Note on BE29: Ivan Protega: On "Investment meeting" 13.06
Note on R33: Ivan Protega: On National Retail meeting for DMs
Note on T33: Ivan Protega: On Country SM meeting for SMs
Note on R38: Ivan Protega: During BP Kick off and National Retail meeting
Note on R44: Ivan Protega: On National Retail meeting for DMs
Note on T44: Ivan Protega: On Country SM meeting for SMs
Note on AD51: Ivan Protega: On CMT meeting 06.12
Note on AS51: Ivan Protega: On CMT meeting 17.03
Note on BE51: Ivan Protega: On CMT meeting 09.06
Note on R53: Ivan Protega: On National Retail meeting for DMs
Note on R54: Ivan Protega: On National Retail meeting for DMs and BP Kick Off for HO
Note on T54: Ivan Protega: On Country SM meeting for SMs
Note on V55: Ivan Protega: On Monthly Retail Meeting 07.10
Note on Z55: Ivan Protega: On National Retail Meeting 06.11
Note on AE55: Ivan Protega: On Monthly Retail Meeting 09.12
Note on AJ55: Ivan Protega: On Monthly Retail Meeting 13.01
Note on AM55: Ivan Protega: On National Retail Meeting 03.02
Note on AQ55: Ivan Protega: On Monthly Retail Meeting 04.03
Note on AV55: Ivan Protega: On Monthly Retail Meeting 07.04
Note on AZ55: Ivan Protega: On Monthly Retail Meeting 06.05
Note on BD55: Ivan Protega: On National Retail Meeting 03.06
Note on BH55: Ivan Protega: On Monthly Retail Meeting 04.07
Note on AD57: Ivan Protega: On CMT meeting 06.12
Note on AS57: Ivan Protega: On CMT meeting 17.03
Note on BE57: Ivan Protega: On CMT meeting 09.06
Note on R59: Ivan Protega: On National Retail meeting for DMs and BP Kick off for HO
Note on T59: Ivan Protega: On Country SM meeting for SMs
Note on V60: Ivan Protega: 09.10. Training and planning
Note on AK61: Ivan Protega: 20.01.2025
Note on AU61: Ivan Protega: 01.04.2025
Note on AD62: Ivan Protega: On CMT meeting 06.12
Note on AS62: Ivan Protega: On CMT meeting 17.03
Note on BE62: Ivan Protega: On CMT meeting 09.06
Note on R65: Ivan Protega: On National Retail meeting for DMs and BP Kick off for HO
Note on T65: Ivan Protega: On Country SM meeting for SMs
Note on AJ66: Ivan Protega: On Monthly Retail Meeting 13.01
Note on AS68: Ivan Protega: On CMT meeting 17.03
Note on BE68: Ivan Protega: On CMT meeting 09.06
Note on V71: Ivan Protega: On Monthly Retail Meeting 07.10
Note on AE71: Ivan Protega: On Monthly Retail Meeting 09.12
Note on AQ71: Ivan Protega: On Monthly Retail Meeting 04.03
Note on AZ71: Ivan Protega: On Monthly Retail Meeting 06.05
Note on AE72: Ivan Protega: 11.12
Note on AQ72: Ivan Protega: 04.03 - 05.03
Note on AD73: Ivan Protega: On CMT meeting 06.12
Note on AS73: Ivan Protega: On CMT meeting 17.03
Note on BE73: Ivan Protega: On CMT meeting 09.06
Note on Y75: Ivan Protega: 28.10 with TAP mentors
Note on AJ75: Ivan Protega: Latest at begining of program with SMT mentors
Note on AM75: Ivan Protega: Latest W6 with TAP mentors for 2nd round
Note on AU75: Ivan Protega: Latest two weeks after Module 2 as preparation for Summer season and peak period
Note on Z76: Ivan Protega: Present status of TAP on NRM 06.11
Note on AM76: Ivan Protega: Present status of SMT on NRM 03.02 (after module 1)
Note on AV76: Ivan Protega: Present status of SMT on NRM 07.04 (after module 2)
Note on BD76: Ivan Protega: Present status of SMT on NRM 03.06 (after module 3)
Note on AE77: Ivan Protega: 11.12
Note on AQ77: Ivan Protega: 04.03 - 05.03
Note on AD78: Ivan Protega: On CMT meeting 06.12
Note on AS78: Ivan Protega: On CMT meeting 17.03
Note on BE78: Ivan Protega: On CMT meeting 09.06
Note on R80: Ivan Protega: On National Retail meeting for DMs and BP Kick off for HO
Note on T80: Ivan Protega: On Country SM meeting for SMs
Note on U81: Ivan Protega: On MCRM 04.10
Note on V81: Ivan Protega: On Monthly Retail Meeting 07.10
Note on Z81: Ivan Protega: On National Retail Meeting 06.11 and Monthly Country RM meeting 05.11
Note on AD81: Ivan Protega: On MCRM 06.12
Note on AE81: Ivan Protega: On Monthly Retail Meeting 09.12
Note on AI81: Ivan Protega: On MCRM 08.01
Note on AJ81: Ivan Protega: On Monthly Retail Meeting 13.01
Note on AL81: Ivan Protega: On MCRM 30.01
Note on AM81: Ivan Protega: On National Retail Meeting 03.02
Note on AQ81: Ivan Protega: On National Retail Meeting 04.03 and Monthly Country RM meeting 03.03
Note on AU81: Ivan Protega: On MCRM 03.04
Note on AV81: Ivan Protega: On Monthly Retail Meeting 07.04
Note on AZ81: Ivan Protega: On National Retail Meeting 06.05 and Monthly Country RM meeting 05.05
Note on BD81: Ivan Protega: On National Retail Meeting 03.06
Note on BH81: Ivan Protega: On Monthly Retail Meeting 04.07
Note on AD83: Ivan Protega: On CMT meeting 06.12
Note on AS83: Ivan Protega: On CMT meeting 17.03
Note on BE83: Ivan Protega: On CMT meeting 09.06
Note on R85: Ivan Protega: On National Retail meeting for DMs and BP Kick off for HO
Note on T85: Ivan Protega: On Country SM meeting for SMs
Note on R86: Ivan Protega: On National Retail meeting for DMs and BP Kick off for HO
Note on T86: Ivan Protega: On Country SM meeting for SMs
Note on AD88: Ivan Protega: On CMT meeting 06.12
Note on AS88: Ivan Protega: On CMT meeting 17.03
Note on BE88: Ivan Protega: On CMT meeting 09.06
Note on R129: Ivan Protega: Secure alignement for each country separately
Note on R139: Ivan Protega: On National Retail meeting for DMs and BP Kick off for HO
Note on T139: Ivan Protega: On Country SM meeting for SMs
Note on X140: Ivan Protega: W43 - 21.10 during SOL meeting
Note on AJ147: Ivan Protega: During QM meeting 16.01
Note on U151: Ivan Protega: During QM meeting 03.10
Note on AJ151: Ivan Protega: During QM meeting 16.01
Note on AU151: Ivan Protega: During QM meeting 02.04
Note on U153: Ivan Protega: During QM meeting 03.10
Note on AJ153: Ivan Protega: During QM meeting 16.01
Note on AU153: Ivan Protega: During QM meeting 02.04
Note on T156: Ivan Protega: On Country SM meeting for XMAS
Note on AR157: Ivan Protega: On Regional SM meeting for Garden
Note on T160: Ivan Protega: Present to SMs on Country SM meeting
Note on U160: Ivan Protega: Present to DMs on MRM in 10.2024
Note on U161: Ivan Protega: Deadline to prepare visit plan
Note on U164: Ivan Protega: On MCRM 04.10
Note on V164: Ivan Protega: On Monthly Retail Meeting 07.10
Note on Z164: Ivan Protega: On National Retail Meeting 06.11 and Monthly Country RM meeting 05.11
Note on AD164: Ivan Protega: On MCRM 06.12
Note on AE164: Ivan Protega: On Monthly Retail Meeting 09.12
Note on AI164: Ivan Protega: On MCRM 08.01
Note on AJ164: Ivan Protega: On Monthly Retail Meeting 13.01
Note on AL164: Ivan Protega: On MCRM 30.01
Note on AM164: Ivan Protega: On National Retail Meeting 03.02
Note on AQ164: Ivan Protega: On National Retail Meeting 04.03 and Monthly Country RM meeting 03.03
Note on AU164: Ivan Protega: On MCRM 03.04
Note on AV164: Ivan Protega: On Monthly Retail Meeting 07.04
Note on AZ164: Ivan Protega: On National Retail Meeting 06.05 and Monthly Country RM meeting 05.05
Note on BD164: Ivan Protega: On National Retail Meeting 03.06
Note on BH164: Ivan Protega: On Monthly Retail Meeting 04.07
Note on V172: Ivan Protega: During DepSM meeting 08.10
Note on AA173: Ivan Protega: Has to be conducted before BF
Note on BB173: Ivan Protega: Has to be conducted before Summer Sale
Note on H180: Igor Opacic: - SM Tips & Tricks – follow up novih stvari (izlaganje na ulazu, PL novi plakati…..itd)
Note on T180: Ivan Protega: On Country SM meeting
Note on Z182: Ivan Protega: On National Retail Meeting 06.11
Note on S185: Ivan Protega: Publish on MYJYSK and send task
Note on S186: Ivan Protega: On Country SM meeting
Note on V186: Ivan Protega: During DepSM meeting 08.10
Note on S191: Ivan Protega: On Country SM meeting
Note on AA195: Ivan Protega: 13.11 during SM meetings in district
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Tips & Tricks:
- Use -/+ button to simplify view
- Use filter buttons to see specific actions (e.g. a specific CSF or actions you are responsible for)

## High-level overview
| 3 | 5 | 2 | 3 | 4 | 6 | 8 | 10 | 11 | 12 | 13
Updated automatically from BP Actions sheet - do not change
BSC | # | CSF Title | BSC Perspective | BSC Focus area | CSF Type | CSF or Action | Responsible | Start | Finish | Comments | Completion rate
| 1 | Fit for the future | Finance | Even better cost management | JYSK | Fit for the future | SSUC
| 2 | Optimise Retail Operations | Internal processes | Attractive stores | JYSK | Optimise Retail Operations | DEL
| 3 | Attract the future | Employees & learning | Attractive place to work | JYSK | Attract the future | JCU
| 4 | Retain and empower our talent and performers | Employees & learning | Attractive place to work | JYSK | Retain and empower our talent and performers | JCU
| 5 | Explore, implement and leverage Artificial Intelligence | Finance | Sales growth | Service function | Explore, implement and leverage Artificial Intelligence
| 6 | Secure the voice of the customer through insights | Finance | Sales growth | Service function | Secure the voice of the customer through insights
| 7 | Make JYSK more sustainable | Finance | Sales growth | Service function | Make JYSK more sustainable
| 8 | Enhance benefits from RTM | Finance | Sales growth | Service function | Enhance benefits from RTM
| 9 | Upgrade web shops to 3.0 | Customer first | Easy shopping | Service function | Upgrade web shops to 3.0
| 10 | Improve delivery stability and service | Internal processes | Balanced flow of goods | Service function | Improve delivery stability and service
| 11 | Simplify communication to stores | Internal processes | Attractive stores | Service function | Simplify communication to stores
| 12 | Improve situation-based marketing and branding | Internal processes | Effective marketing | Service function | Improve situation-based marketing and branding
| 13 | Make “Great offers” more visible | Internal processes | Effective marketing | Service function | Make “Great offers” more visible
| 14 | Improve online performance | Customer First | Easy shopping | Local | Improve online performance | IPR
| 15 | Optimize stock in stores | Internal processes | Attractive stores | Local | Optimize stock in stores | MSTEV
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Quick guide
Quick guide
Excel sheet:
Creating CSFs
Whole numbers in column "#" indicate a CSF
2
BP actions
High-level overview
Use the BP Actions sheet to:
- Define CSFs and actions
- Define responsible, participants and deadline
- Update ongoing status on specific actions
Meta data
Fill out in all rows to use filters/slicers
BSC perspective and focus area
CSF type and Title
1
Creating actions for CSF
Example: #4 Implement DM 3.0
Actions indicated with 4.1, 4.2 etc.
Sub-actions indicated with 4.1.1, 4.1.2 etc.
3
Use the High-level overview sheet to:
- Have an auto-updated overview of CSFs
- Ongoing follow-up on status
OBS: High-level overview is automatically updated based on BP Actions sheet
Step-by-step guide
CSF example
x

## Backend (hidden)
Completion rate
Type of CSF | Perspective | Focus Area | Finance | Customer first | Internal processes | Employees & learning |  | 100%
JYSK | Finance | Even better cost management | Even better cost management | Reliable product quality | Balanced flow of goods | Strong talent pipeline | Even better cost management | 75%
Service Function | Customer first | Improve earnings | Improve earnings | Easy shopping | Relevant assortment | Relevant training | Improve earnings | 50%
Local | Internal processes | Sales growth | Sales growth | Competent service | Attractive stores | Great store management | Sales growth | 25%
| Employees & learning | Expansion | Expansion | Seamless cross channel | Effective marketing | Attractive place to work | Expansion | Not started
|  | Reliable product quality |  |  |  |  | Reliable product quality | Not relevant
|  | Easy shopping |  |  |  |  | Easy shopping
|  | Competent service |  |  |  |  | Competent service
|  | Seamless cross channel | RGB |  |  |  | Seamless cross channel
|  | Balanced flow of goods | 252 | 197 | 176 | 223 | Balanced flow of goods
|  | Relevant assortment | 209 | 222 | 203 | 142 | Relevant assortment
|  | Attractive stores | 99 | 239 | 169 | 120 | Attractive stores
|  | Effective marketing |  |  |  |  | Effective marketing
|  | Strong talent pipeline |  |  |  |  | Strong talent pipeline
|  | Relevant training |  |  |  |  | Relevant training
|  | Great store management |  |  |  |  | Great store management
|  | Attractive place to work |  |  |  |  | Attractive place to work
Formulas for conditional formatting of perspectives
FALSE
FALSE
FALSE
FALSE